## Roadmap and Status
Sno | Component | Platform | Quarter started | Task | Developer | Status | Comments
1 | CMCardConnect | iOS | Q2-2020 | Initial | Ramesh | Done
2 | CMCardConnect | Android | Q2-2020 | Initial | Vaishali | Done
2 | CMGooglePay | iOS | Q2-2020 | Initial | Akshay | Done
3 | CMApplePay | Android | Q2-2020 | Initial | Ramesh | Done
3 | CMKeypad | iOS | Q2-2020 | Enhancement. Make it similar to Android | Afsar | Done | Documentation pending
4 | CMTextInput | Android | Q2-2020 | Enahncement to incorporate multiple types by Password, Zip, Phone number, SSN, Regex | Ashok | Done | Documentation pending
4 | CMTextInput | iOS | Q2-2020 | Enahncement to incorporate multiple types by Password, Zip, Phone number, SSN, Regex | Akash | 20%
5 | CMButton | iOS | Q2-2020 | Enhancements to support multiple design options | Dheeraj | Done
6 | CMView | iOS | Q2-2020 | Enhancements to support multiple design options | Dheeraj | Done
7 | CMStepBar | iOS | Q2-2020 | New development | Laxman | Done
8 | CMSegment | iOS | Q2-2020 | New development | Laxman | Done
9 | Apple Pay | iOS | Q3-2020 | Initial | Ramesh | Done
10 | Google Pay | Android | Q3-2020 | Initial | Akshay | Done
11 | CMTextInput | React Native | Q3-2020 | Initial | Ashok | Done
12 | CMDatePicker | React Native | Q3-2020 | Initial | Ashok | Done
13 | CMSearch | React Native | Q3-2020 | Initial | Ashok | Done
14 | CMAlert | React Native | Q3-2020 | Initial | Ashok | Done
15 | CMSelect | React Native | Q3-2020 | Initial | Akbar | Done
16 | CMProgressLoader | React Native | Q3-2020 | Initial | Akbar | Done
17 | CMWebView | React Native | Q3-2020 | Initial | Akbar | Done
18 | CMAppToolBar | React Native | Q3-2020 | Initial | Akbar | Done
19 | CMBiometric | React Native | Q3-2020 | Initial | Akbar and Akash, Alam | Done
20 | CMTextInput | iOS | Q4-2020 | Enahncement to incorporate multiple types by Password, Zip, Phone number, SSN, Regex
21 | CMButton | Android | Q4-2020 | Enhancements to support multiple design options
22 | CMView | Andriod | Q4-2020 | Enhancements to support multiple design options similar to iOS
23 | CMStepBar | Android | Q4-2020 | Similar to iOS
24 | CMSegment | Android | Q4-2020 | Similar to iOS
25 | CMStepBar | Android | Q4-2020 | New development
26 | CMSegment | Android | Q4-2020 | New development
27 | CMTextInput | Xamarin | Q4-2020
28 | CMDatePicker | Xamarin | Q4-2020
29 | CMSearch | Xamarin | Q4-2020
30 | CMAlert | Xamarin | Q4-2020
31 | CMSelect | Xamarin | Q4-2020
32 | CMProgressLoader | Xamarin | Q4-2020
33 | CMWebView | Xamarin | Q4-2020
34 | CMButton | Xamarin | Q4-2020
35 | CMForm | iOS | Q1, Q2-2021
36 | CMForm | Android | Q1, Q2-2021
37 | CMForm | React Native | Q1, Q2-2021
38 | CMForm | Xamarin | Q1, Q2-2021
39 | CMAuthentication | iOS | Q1, Q2-2021 | Basic, Bearer Token
40 | CMAuthentication | Android | Q1, Q2-2021 | Basic, Bearer Token
41 | CMAuthentication | React Native | Q1, Q2-2021 | Basic, Bearer Token
42 | CMAuthentication | Xamarin | Q1, Q2-2021 | Basic, Bearer Token
43 | CMListScreen | iOS | Q1, Q2-2021
44 | CMListScreen | Android | Q1, Q2-2021
45 | CMListScreen | React Native | Q1, Q2-2021
46 | CMListScreen | Xamarin | Q1, Q2-2021
47 | CMPagination | iOS | Q1, Q2-2021
48 | CMPagination | Android | Q1, Q2-2021
49 | CMPagination | React Native | Q1, Q2-2021
50 | CMPagination | Xamarin | Q1, Q2-2021
51 | CMMasterDetail | iOS | Q3-2021
52 | CMMasterDetail | Android | Q3-2021
53 | CMMasterDetail | React Native | Q3-2021
54 | CMMasterDetail | Xamarin | Q3-2021
55 | Update CMMasterDetail in project | iOS | Q4-2021
56 | Update CMMasterDetail in project | Android | Q4-2021
57 | Update CMMasterDetail in project | React Native | Q4-2021
58 | Update CMMasterDetail in project | Xamarin | Q4-2021

## Development Log
2019 Q3
Sno | Component | Platform | Developer | Notes | Project Contributed
1 | CMButton | Android | Ashok | Initial | BW
2 | CMButton | iOS | Akash | Initial | BW
3 | CMTextInput | Android | Ashok, Abdhesh | Initial | BW
4 | CMTextField | iOS | Akash, Laxman | Initial | BW
5 | Biometric | Android | Pratiti | Initial | BW
6 | CMProgressbar | Android | Rakesh Jha | Initial | BW
7 | CMNetworkHelper | iOS | Sowjanya | Initial | BW
8 | CMProgressbar | iOS | Anshu Sharma | Initial
2019 Q4
Sno | Component | Platform | Developer | Notes | Project Contributed/Used
1 | CMButton | Android | Akshay | made more configurable | BW, Ezpass, WellCheck 1.0
2 | CMButton | iOS | Narasimha | made more configurable | BW, Ezpass, WellCheck 1.0
3 | CMKeypad | Android | Akshay | Initial | EZPass
4 | CMKeypad | iOS | Narasimha | Initial | EZPass
5 | CMBiometric | iOS | Narasimha | Initial | EZPass
6 | CMBiometric | Android | Gopal Anand | added face | EZPass
7 | CMTextInput | Android | Akshay | made more configurable | BW, Ezpass, WellCheck 1.0
8 | CMTextInput | iOS | Pardhu | made more configurable | BW, Ezpass, WellCheck 1.0
9 | CMGradientView | iOS | Narasimha | Initial | EZPass
10 | CMGradientView | Android | Akshay | Initial | EZPass
11 | CMSearchView | Android | Akshay | Initial | EZPass
12 | CMStepView | Android | Akshay | Initial | EZPass
13 | CMTimeInput | Android | Akshay | Initial | EZPass
14 | CMDropDownView | Android | Akshay | Initial | EZPass
15 | CMCenteredIconButton | Android | Akshay | Initial | EZPass
16 | CMGradientView | iOS | Narasimha | Initial | EZPass
17 | CMSearchView | iOS | Narasimha | Initial | EZPass
18 | CMStepView | iOS | Narasimha | Initial | EZPass
19 | CMTimeInput | iOS | Narasimha | Initial | EZPass
20 | CMDropDownView | iOS | Narasimha | Initial | EZPass
21 | CMCenteredIconButton | iOS | Narasimha | Initial | EZPass
22 | CMDevice | iOS | Narasimha | Initial | EZPass
23 | CMDevice | Android | Akshay | Initial | EZPass
24 | CMToolbar | iOS | Narasimha | Initial | EZPass, WellCheck 1.0
25 | CMLabel | iOS | Narasimha | Initial | EZPass, WellCheck 1.0
26 | CMView | iOS | Narasimha | Initial | EZPass
27 | CMStackView | iOS | Alam | Initial | EZPass
28 | CMSearchView | iOS | Ramesh | Initial | EZPass
29 | CMToolbar | Android | Akshay | Initial | EZPass, WellCheck 1.0
30 | CMLabel | Android | Akshay | Initial | EZPass, WellCheck 1.0
31 | CMView | Android | Akshay | Initial | EZPass
32 | CMStackView | Android | Akshay | Initial | EZPass
33 | CMSearchView | Android | Akshay | Initial | EZPass
34 | CMCalender | iOS | Afsar | Initial | ECC
35 | CMCalender | Android | Venkat | Initial | ECC
36 | CMDateInput | Android | Pratiti | Initial | BW, Ezpass, WellCheck 1.0
37 | CMDateInput | iOS | Ramesh | Initial | BW, Ezpass, WellCheck 1.0
2020 Q1
Sno | Component | Platform | Developer | Notes | Project Contributed
1 | MultilineTextInput | iOS | Akash | Initial | BW
2 | MultilineTextInput | Android | Ashok | Initial | BW
3 | CMCardConnect | iOS | Ramesh | Initial | EZpass
4 | CMCardConnect | Android | Anand | Initial | EZpass
5 | CMLicencePlateReaderALPR | Android | Akshay | Initial | EZpass
6 | CMLicencePlateReaderALPR | iOS | Ramesh | Initial | EZpass
7 | CMFirebaseEventLogger | Android | Vaishali | Initial | EZpass
8 | CMFirebaseEventLogger | iOS | Alam | Initial | EZpass
9 | CMBarcodeScanner | Android | Prathyusha | Initial | EZpass
10 | CMBarcodeScanner | iOS | Narasimha | Initial | EZpass
11 | CMImageHelper | iOS | Ramesh | Initial | EZpass
12 | CMImageHelper | Android | Akshay | Initial | EZpass
13 | CMNetworkHelper | iOS | Sowjanya | Updated to handle additional cases | Ezpass, BW
14 | CMNetworkHelper | Android | Akbar, Akshay | Updated to handle additional cases | Ezpass, BW
2020 Q2
Sno | Component | Platform | Developer | Notes | Project Contributed
1 | CMTextInput | Android | Ashok | Integrated multiple components like CMText, CMSSN, CMZip
2 | CMSegment | iOS | Laxman | Made it generic and added to support custom shapes and view
3 | CMStepProgress | iOS | Laxman | Made it generic and added to support custom shapes and view
4 | CMButton | iOS | Dheeraj | Made it more configurabel to support image, gradient, image. Integrated multiple components into 1
5 | CMView | iOS | Dheeraj | Added as an interface. Can be added to any display control
6 | CMKeyPad | iOS | Afsar | Made it similar to Android
2020 Q3
Sno | Component | Platform | Developer | Notes | Project Contributed
1 | CMTextInput | React Native | Ashok | Initial | WellCheck 2.0
2 | CMDatePicker | React Native | Ashok | Initial | WellCheck 2.0
3 | CMSearch | React Native | Ashok | Initial | WellCheck 2.0
4 | CMAlert | React Native | Ashok | Initial | WellCheck 2.0
5 | CMSelect | React Native | Akbar | Initial | WellCheck 2.0
6 | CMProgressLoader | React Native | Akbar | Initial | WellCheck 2.0
7 | CMWebView | React Native | Akbar | Initial | WellCheck 2.0
8 | CMAppToolBar | React Native | Akbar | Initial | WellCheck 2.0
9 | CMBiometric | React Native | Akbar and Akash | Initial | WellCheck 2.0
2020 Q4
Sno | Component | Platform | Developer | Notes | Project Contributed
1 | CMTextInput | Xamarin
2 | CMDatePicker | Xamarin
3 | CMSearch | Xamarin
4 | CMAlert | Xamarin
5 | CMSelect | Xamarin
6 | CMProgressLoader | Xamarin
7 | CMWebView | Xamarin
8 | CMAppToolBar | Xamarin
9 | CMBiometric | Xamarin
10
11

## Matrix - Dev
SNo | Component | iOS | Android | ReactNative | Xamarin
1 | CMTextInput | Akash | Ashok | Ashok | TBD
2 | CMButton | Dheeraj | Akshay | Ashok | TBD
3 | CMCalender | Afsar | Venkat | TBD | TBD
4 | CMKeypad | Afsar | Akshay | TBD | TBD
5 | CMNetwork | Sowjanya | Akbar | Ashok | TBD

## Matrix - Usage
SNo | Component | iOS | Android | React Native | Xamarin
1 | CMTextInput
2 | CMButton
3 | CMCalender
4 | CMKeypad
5 | CMNetwork